## Indent Tracker
TGMSIDC End-to-End Indent Tracker
Indent | [10 empty] | RC Position |  |  | Tender stage |  | Purchase Order | Supply Status
Sl. No | Inward No | Indent No | District | Hospital | HOD | Indent Date | Equipment Name | Equipment Type | Quantity | Prioritization | Budget Sanction | Case Worker | Rate Contract | Tender No | Tender Stage | PO No | Supplied Qty | Pending Qty | Supplied
1 | 21391 | IND 1001 | Mancherial | AH, Chennur | TVVP | 02.04.2026 | CT Siemens 16 Slice | Equipment | 1 | Required | 2000000 | Rajesh | Available |  |  | 22A | 1 | 0 | Yes
2 | 21391 | IND 1001 | Mancherial | AH, Chennur | TVVP | 02.04.2026 | MRI Siemens 1.5 Tesla | Equipment | 4 | Required |  | Rajesh | Not Available | TEN123 | Tender Published | 22A | 2 | 2 | Yes
3 | 21391 | IND 1001 | Mancherial | AH, Chennur | TVVP | 02.04.2026 | Work station Machine | Furniture | 10 | Required |  | Rajesh | Available |  |  | 22A | 10 | 0 | No
4 | 21391 | IND 1001 | Mancherial | AH, Chennur | TVVP | 02.04.2026 | Multi para monitors | Equipment | 1 | Reprioritization Sent - Awaiting Reply |  | Rajesh | Available |  |  | 22A | 1 | 0 | Yes
5 | 21391 | IND 1001 | Mancherial | AH, Chennur | TVVP | 02.04.2026 | ESWL Machine with Monitor | Equipment | 1 | Required |  | Rajesh | Available |  |  | 22A | 1 | 0 | Yes
6 | 21391 | IND 1002 | Mancherial | AH, Chennur | TVVP | 28.04.2026 | Laparoscopic Camera | Equipment | 4 | Required | 4000000 | Muneendra | Not Available | TEN123 | Pre-Bid Stage |  |  | 4 | No
7 | 22326 | IND 1002 | Nizamabad | DH Bodhan | TVVP | 28.04.2026 | Autoclaves | Equipment | 3 | Required |  | Muneendra | Not Available | TEN123 | Bid Submission Open |  |  | 3 | No
8 | 22326 | IND 1002 | Nizamabad | DH Bodhan | TVVP | 28.04.2026 | Defibrillator | Equipment | 1 | Not Required |  | Muneendra | Available |  |  | 23A | 1 | 0 | Yes
9 | 22326 | IND 1002 | Nizamabad | DH Bodhan | TVVP | 28.04.2026 | Ceiling Shadow less lamp | Equipment | 1 | Required |  | Muneendra | Available |  |  | 23A | 1 | 0 | Yes
Note on I3: Dropdown: Equipment or Furniture.
Note on K3: Dropdown: Required or Not Required.
Note on N3: Dropdown values: Available, Not Available, Expired, or Not Applicable. Use Available only when an active RC exists for the item.
Note on P3: Select the current tender stage. BFC Approved means the tender is finalized. Use Partially BFC Approved when only some tender items are finalized.
Note on S3: Calculated automatically: Quantity minus Supplied Qty.
Note on T3: Dropdown: Yes or No.

## Dropdown Lists (hidden)
Equipment Type | Prioritization | Supplied | Rate Contract | Tender Stage
Equipment | Required | Yes | Available | Not Initiated
Furniture | Not Required | No | Not Available | Specification Confirmation
| Reprioritization Sent - Awaiting Reply |  | Expired | Tender Drafting
|  |  | Validity Under Verification | Tender Published
Pre-Bid Stage
Bid Submission Open
Bid Closed
Bid Opening
Technical Evaluation
Demonstration Stage
Financial Evaluation
Pending BFC
BFC Approved
Partially BFC Approved
BFC Deferred
Recalled
Retendered
Cancelled
Closed